## JQL
Issue Type | Key | Summary | Assignee | Priority | Status | Resolution
Task | CT-14110 | Automation task_Sameera Sprint1 | Sameera De Silva | Medium | Ready for Planning
Task | CT-14074 | Automation task_Winky | Winky Nan | Medium | Ready for Planning
Task | CT-14069 | Automation task_Lily_Sprint1 | Lily Tian | Medium | Ready for Planning
Task | CT-14042 | FY27Q1 Sprint1 Prod Support | Priyanga Arachchi | P3 (Normal) | Ready for Planning
Task | CT-14015 | Optimize of Dates of filter panel on overview pages (SI/SIP/GSI/GSIP) | Elwin Sun | High | Ready for Planning
Task | CT-13948 | Upgrade Spring boot to 4.0.5 | Kexin Guo | P3 (Normal) | Ready for Planning
Task | CT-13914 | Optimize of Dates of Generic SIP detail page | Elwin Sun | High | Ready for Planning
Story | CT-13869 | [Research] Technical design of Async API for SIP Events API | Kexin Guo | Minor | Ready for Planning
Story | CT-13824 | (Generic) Add SIP code to SI details page | Kexin Guo | P3 (Normal) | Ready for Planning
Task | CT-13758 | Update Publication detail headers | Wenxi Li | P3 (Normal) | Ready for Planning
Story | CT-13406 | Export Unpublished or Open SIs Acquired Before 6 March 2025 | Aradhana Mistry | P3 (Normal) | To Do
Story | CT-13235 | SIP source tracking | Yuxin Wang | High | Ready for Planning
Story | CT-10354 | Generic Workflow - GE Information link to GE Details page | Yuxin Wang | P3 (Normal) | Ready for Planning

## Summary
|  | Sprint | Date | Story Count (need testing) | New Test Case Count | Test Run Cases Count (it may include regression cases) | Submitted Bug Count
Story Points | Working days | FY26 Q1 - Sprint 1 | 4.30-5.14 | 6 | 57 | 68 | 18
1 | <=0.5 days | FY26 Q1 - Sprint 2 | 5.14-5.28 | 8 | 175 | 250 | 56
2 | > 0.5 day and <=1 days | FY26 Q1 - Sprint 3 | 5.28-6.11 | 8 | 105 | 145 | 28
3 | > 1 day and <=3 days | FY26 Q1 - Sprint 4 | 6.11-6.25 | 8 | 129 | 168 | 55
5 | > 3 day and <=6 days | FY26 Q1 - Sprint 5 | 6.25-7.9 | 8 | 73 | 73 | 36
8 | > 6 day and <=10 days | FY26 Q1 - Sprint 6 | 7.9-7.23 | 10 | 100 | 135 | 16
|  | July 17th release UAT | 7.9-7.16 | 14 | 0 | 173 | 5
|  | August 7th release UAT | 7.25-7.29 | 8 | 0 | 126 | 6
|  | FY26 Q2 - Sprint 1 | 8.07-8.13 | 8 | 40 | 40 | 13
|  | August 21st release UAT | 8.13-8.15 | 9 | 0 | 82 | 0
|  | FY26 Q2 - Sprint 2 | 8.22-8.27 | 7 | 0 | 316 | 11
|  | FY26 Q2 - Sprint 3 | 8.22-9.10 | 7 | 0 | 415 | 20
|  | FY26 Q2 - Sprint 4 | 9.10-9.24 | 11 | 14 | 358 | 25
|  | FY26 Q2 - Sprint 5 | 9.24-10.8 | 9 | 5 | 93 | 5
|  | FY26 Q2 - Sprint 6 | 10.9-10.22 | 10 | 19 | 112 | 18
|  | FY26Q3 - Sprint 1 | 10.29-11.12 | 9 | 49 | 57 | 2
|  | FY26Q3 - Sprint 2 | 11.12-11.25 | 10 | 9 | 80 | 37
|  | FY26Q3 - Sprint 3 | 11.26-12.09 | 13 | 102 | 102 | 25
|  | FY26Q3 - Sprint 4 | 12.20-12.23 | 10 | 18 | 184 | 79
|  | FY26Q3 - Sprint 5 | 1. 6-1. 20 | 12 | 61 | 61 | 24
|  | FY26Q3- UAT Multi | 1.20-1.22 | 103 | 0 | 175 | 33
|  | JIRA Query | Bug - Sprint | Follow

## FY27Q1
Sprint | Time | Type | ID | Title | DEV SP | Assignee | QA Man days | Automated | Comments
Sprint1 | April 29-May 12 | Task | CT-14015 | Optimize of Dates of filter panel on overview pages (SI/SIP/GSI/GSIP) |  | Sameera
|  | Task | CT-13948 | Upgrade Spring boot to 4.0.5 |  | Sameera
|  | Task | CT-13914 | Optimize of Dates of Generic SIP detail page |  | Sameera
|  | Story | CT-13824 | (Generic) Add SIP code to SI details page |  | Lily
|  | Task | CT-13758 | Update Publication detail headers |  | Winky
|  | Story | CT-13235 | SIP source tracking |  | Chanaka
|  | Story | CT-10354 | Generic Workflow - GE Information link to GE Details page |  | Chanaka
Sprint2 | May 13-May 26 | Story | CT-14060 | Generic - SIP Details - Create - SIP Supplementary Files Section
|  | Task | CT-14058 | SCA SIP Overview page optimize
|  | Task | CT-14057 | Update the periodical job health email and add correct developer email in the recipent list
|  | Story | CT-13985 | SCA - Notification emails for EBM review progress
|  | Story | CT-13982 | SCA - EBM Review Panel - Always open and editable
|  | Story | CT-13959 | Generic - Notification emails for 'completion' of JE review
|  | Story | CT-13907 | Generic - Notification emails for EBM review progress
|  | Story | CT-13880 | CLONE - [Impl] SI Event sending - deleting
|  | Story | CT-13876 | [Impl] SIP Event sending - updating
|  | Story | CT-13871 | [Impl] SIP Event sending - creation
|  | Story | CT-13868 | [Impl] Generic SIP Event sending - deleting
|  | Story | CT-13865 | CLONE - Generic SIP Kafka Topic creation and connectivity testing for all envs
|  | Story | CT-13411 | Test Curate Events to Ensure SI Records Now Include the ReX‑Review UUID
|  | Story | CT-13410 | Update Curate SI Record UUID Using Matched Review SI UUIDs
|  | Story | CT-12556 | Generic/SCA- Notify Stakeholders After GE Invitation Response
|  | Story | CT-7447 | SCA solicited & Unsolicited Workflow - SIP Details - Create - SIP Supplementary Files Section
Sprint3 | May 26- June 9 | Task | CT-14022 | SCA - Remove LGE add/remove GE permissions at revision unless origin is ideation
|  | Task | CT-14011 | Perf tuning - api- getSpeicalIssueBySiCode
|  | Task | CT-13989 | Add production details back into email templates
|  | Task | CT-13988 | Populate production details in exported data
|  | Task | CT-13987 | Populate production details in SI/P details page from RPM
|  | Task | CT-13986 | Consume PM and production office contact
|  | Story | CT-13983 | Allow EBMs to be re-invited after revision
|  | Story | CT-13981 | SCA/Generic - Refine EBM Review Comments display and interaction
|  | Story | CT-13971 | 6. Allow Curation Type to be edited up to acquisition with GE re‑screening
|  | Story | CT-13970 | 7. Maintain collection handling functionality on SSIP flow
|  | Story | CT-13969 | 3. Remove Guest Editor section for Thematic Issues and Collections
|  | Story | CT-13910 | GE details should be blank in SI/SIP overview dashboards where curation type = thematic issue
|  | Story | CT-13909 | Allow filtering on Curation type from SIP/SI overview dashboard
|  | Story | CT-13905 | 4. Suppress GE‑specific communications for GE‑free curation
|  | Story | CT-13904 | 5. Revision decision is disabled if curation type = thematic issue
|  | Story | CT-13903 | 2. GE checks should not be shown/required when curation type=thematic issue/collection
|  | Story | CT-13902 | 1. Move curation type input to Ideation stage and editable in stages following
|  | Story | CT-13234 | Exclude Personal Data from GE Overview Page Export
|  | Story | CT-13232 | Exclude Personal Data from SIP/SSIP Overview Page Export
|  | Story | CT-13231 | Exclude Personal Data from SI Overview Page Export

## FY26Q4
Sprint | Time | Type | ID | Ready for UAT | Epic | Title | DEV SP | Assignee | QA Man days | Automated | Comments
Sprint1 | Jan 28 - Feb 10 | Task | CT-13210 |  | CT-13359Keep The Lights On - FY26Q4 | Missed things that need to be done before release multi-tenancy
|  | Story | CT-13071 |  | CT-11273Generic SIP workflow MVP Phase 1 | [BE Decision] Manage SIP in ideation |  | Winky
|  | Story | CT-13070 |  | CT-11273Generic SIP workflow MVP Phase 1 | [BE Ge Update] Manage SIP IN Ideation | GE add update not include invitation | Sameera
|  | Story | CT-13069 |  | CT-11273Generic SIP workflow MVP Phase 1 | [BE Update] Manage SIP In Ideation | Include Special Issue Proposal details, Dates and Content Commissioning Approaches | Sameera
|  | Story | CT-13068 |  | CT-11273Generic SIP workflow MVP Phase 1 | [FE Decision Panel] Manage SIP In Ideation |  | Winky
|  | Story | CT-13067 |  | CT-11273Generic SIP workflow MVP Phase 1 | [FE SIP history] Manage SIP In Ideation | Include SIP Editing History,GE editing history and email history | Winky
|  | Story | CT-13066 |  | CT-11273Generic SIP workflow MVP Phase 1 | [FE GE Information]Manage SIP in Ideation Stage |  | Sameera
|  | Task | CT-12695 |  |  | Config the Prod domain name
|  | Story | CT-12160 |  | CT-11273Generic SIP workflow MVP Phase 1 | Display SIP Details Page |  | Lily
|  | Story | CT-11600 |  | CT-11273Generic SIP workflow MVP Phase 1 | [FE Basic info]Manage SIP in Ideation Stage | Include Special Issue Proposal details, Dates and Content Commissioning Approaches | Sameera
|  | Story | CT-11599 |  | CT-11273Generic SIP workflow MVP Phase 1 | Create SIP Overview Table and Filters |  | Lily
|  | Story | CT-9341 |  | CT-9021EBM Review Suggestion Tool | EBM Review - EBM Suggestion Tool |  | Lily |  |  | 34+regression
Sprint2 | Feb 11-Feb 24 | Story | CT-13462 |  | CT-12732 Generic SIP workflow MVP Phase 1 | Screening Stage: add "Screening Checks" in decision API response |  | Winky
|  | Story | CT-13457 |  | CT-12732 Generic SIP workflow MVP Phase 1 | Screening Stage: Decision Panel |  | Winky
|  | Story | CT-13454 |  | CT-12732 Generic SIP workflow MVP Phase 1 | [BE]AI Screening in Screening Checklist Page |  | Sameera
|  | Story | CT-12161 |  | CT-12732 Generic SIP workflow MVP Phase 1 | Manage SIP in Screening Stage |  | Sameera
Sprint3 | Feb25-March 10 | Improvement | CT-13475 |  |  | [Multi-tenancy] Add journal manager's and PM 's journal list change in system log |  | Lily
|  | Story | CT-13458 |  |  | [Checklist Status]Screening checklist page for Generic SIP workflow |  | Winky
|  | Story | CT-13460 |  |  | Screening Stage: New GEs reminder |  | Winky
|  | Story | CT-13454 |  |  | [BE]AI Screening in Screening Checklist Page |  | Sameera
|  | Story | CT-13453 |  |  | [FE]AI Screening in Screening Checklist Page |  | Sameera
|  | Story | CT-13456 |  |  | [Download] Download AI Screening Report |  | Sameera
|  | Story | CT-13393 |  |  | [Checklist Detail]Screening checklist page for Generic SIP workflow |  | Lily
Sprint4 | March11-March24 | Story | CT-13486 |  |  | Guest Editor invitation response (Generic SIP2) |  | Sameera
|  | Story | CT-13304 |  |  | Review Stage: Submit Decision |  | Winky
|  | Story | CT-13302 |  |  | Review Stage: Initiate Editorial Board Member Review via manual invitation |  | Lily
|  | Story | CT-13301 |  |  | Review Stage: Decision Panel Visibility (Generic SIP2) |  | Winky
|  | Story | CT-13300 |  |  | Review Stage: Edit Dates (Generic SIP2) |  | Winky
|  | Story | CT-13299 |  |  | Review Stage: Edit Content Commissioning Approaches (Generic SIP2) |  | Lily
|  | Story | CT-13297 |  |  | Invite Guest Editors (Generic SIP2) |  | Sameera
|  | Story | CT-13296 |  |  | Review Stage: Edit SIP Title and Details (Generic SIP2) |  | Winky
|  | Story | CT-12166 |  |  | Allow Clearing of SCA Lead and SCA Manager Fields |  | Lily
|  | Story | CT-12165 |  |  | Clear SCA Fields on Journal Opt-Out |  | Sameera
Sprint5 | March25-April7 | Task | CT-13737 |  |  | Invite GE automation jobs + reminder |  | Sameera
|  | Task | CT-13733 |  |  | Multi-Tenancy Performance Test |  | Huixin
|  | Story | CT-13491 |  |  | Review Stage: Initiate Editorial Board Member Review via EBM suggestion tool invitation |  | Lily
|  | Story | CT-13309 |  |  | Withdrawn Stage |  | Lily
|  | Story | CT-13308 |  |  | Rejected Stage |  | Winky
|  | Story | CT-13307 |  |  | Accepted Stage |  | Winky
|  | Story | CT-13306 |  |  | Revision Stage: Lead GE |  | Sameera
|  | Story | CT-13305 |  |  | Revision Stage: Proposal Manager |  | Sameera
|  | Story | CT-13303 |  |  | Review Stage: Initiate Journal Editor Decision |  | Winky |  | N/A, Yes, Under Development
Sprint6 | April8-April21 | Story | CT-13861 |  |  | CLONE - Username & User Profile Synchronization Between Curate and CONNECT |  | Lily
|  | Task | CT-13859 |  |  | Perf tuning - api- getSpeicalIssueBySiCode - Phase1 |  | Lily
|  | Task | CT-13858 |  |  | Perf tuning - api- specialIssueFilter - Phase1 |  | Lily
|  | Task | CT-13554 |  |  | Open for submission date should be removed from Ideation and Screening stage |  | Winky
|  | Story | CT-13311 |  |  | Username & User Profile Synchronization Between Curate and CONNECT |  | Lily
|  | Improvement | CT-13236 |  |  | Incorrect wording on COI declaration- SCA SSIP creation |  | Winky
|  | Story | CT-13097 |  |  | Role based access to SI/Ps
|  | Task | CT-13064 |  |  | Optimize of Dates of Generic SI detail page |  | Sameera |  | Winky will help Sameera execute it while he is on vacation.
|  | Task | CT-13062 |  |  | Optimize of Dates when acquired SI |  | Sameera |  | Winky will help Sameera execute it while he is on vacation.
|  | Task | CT-13061 |  |  | Optimize of Dates of SIP detail page |  | Sameera |  | Winky will help Sameera execute it while he is on vacation.
|  | Task | CT-11886 |  |  | Optimize of Dates of SI detail page |  | Sameera |  | Winky will help Sameera execute it while he is on vacation.
|  | Story | CT-10352 |  |  | (Generic) GE Details Page - Add Associated Special Issue Proposals table |  | Lily
|  | Story | CT-10351 |  |  | Create GE Profiles starting in the Generic SIP workflow
|  | Improvement | CT-8909 |  |  | Collect COI per GE in USIP form |  | Winky
IP Week | April22-April28 | Story | CT-13540 |  |  | Email templates for Generic SIP workflow |  | Sameera
|  | Story | CT-13822 |  |  | Add Email templates for Generic SIP workflow to tenant admin admin page |  | Sameera
|  | Story | CT-13704 |  |  | Screening Stage: Auto‑cancel open GE invites when moving submission to Review at Screening stage |  | Lily
|  | Task | CT-14014 |  |  | Optimize of Dates - periodical-task trigger moment update |  | Winky

## FY26Q3
Sprint | Time | Type | ID | Ready for UAT | Epic | Title | DEV SP | Assignee | QA Man days | Comments
Sprint1 | 29-Oct-2025 12-Nov-2025 | Task | CT-12739 | Closed | [Multi-Tenancy] Tenant ID resolving & processing | Discovery - Rex Review And Submission Integrate Testing. | 1 |  |  | No need to test
|  | Task | CT-12738 | Closed | [Multi-Tenancy] Platform Admin Portal | [Research] Save the Connect Secret into AWS Secret Manager by APP | 3 |  |  | No need to test
|  | Task | CT-12681 | Closed | [Multi-Tenancy] Tenant Admin Portal | [S3][download]Streamlined Download of Generated Files via S3 and SSE with Request Deduplication | 5 |  |  | No need to test in Sprint1, will test it in Sprint2
|  | Task | CT-12680 | Closed | [Multi-Tenancy] Tenant Admin Portal | [S3][download] Enable Direct File Downloads via S3 Pre-Signed URLs | 5 |  |  | No need to test in Sprint1, will test it in Sprint2
|  | Task | CT-12664 | Closed | Tech Debt - Performance tuning FY26Q3 | Merge duplicated class - part 1 | 3 |  |  | No need to test, Elwin will test it by himself
|  | Task | CT-12575 | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Assess impact of tenantId injection on non-generic events and schedulers - [Phase 2] | 5 | Lily/Winky/Sameera
|  | Task | CT-11995 | Yes | [Multi-Tenancy] Tenant Admin Portal | email template page | 2 | Sameera
|  | Task | CT-11993 | Yes | [Multi-Tenancy] Tenant Admin Portal | user management page | 2 | Winky
|  | Task | CT-11992 | Yes | [Multi-Tenancy] Tenant Admin Portal | Role displaying page | 2 | Lily
Sprint2 | 11-Nov-2025 25-Nov-2026 | Task | CT-12739 | Closed | [Multi-Tenancy] Tenant ID resolving & processing | Discovery - Rex Review And Submission Integrate Testing. |  |  |  | No need to test
|  | Task | CT-12736 | Yes | [Multi-Tenancy] Platform Admin Portal | [API] Get Tenants API | 2 | Sameera |  | Can be tested in Sprint3 with platform admin
|  | Task | CT-12733 | Yes | [Multi-Tenancy] Platform Admin Portal | [API] Get tenant admin API | 1 | Sameera |  | Can be tested in Sprint3 with platform admin
|  | Task | CT-12722 | Yes | Tech Debt - Performance tuning FY26Q3 | [S3][download] Replace the old download method to the New File Download Method |  | Lily/Winky/Sameera |  | Regression testing need to cover 53 cases https://wiley-global.atlassian.net/wiki/spaces/CTC/pages/77980690/S3+File+Generation+and+Pre-signed+Link+Download+Workflow+Design
|  | Task | CT-9370 | Yes | Tech Debt - Performance tuning FY26Q3 | [S3][Upload] Integrate all file upload functions into one set of logic. | 5 | Sameera
|  | Task | CT-12047 | Yes | [Multi-Tenancy] Platform Admin Portal | [FrontEnd] Platform Admin Menu | 1 | Winky |  | We can only see Platform Admin menu, page is empty in Sprint2
|  | Task | CT-12042 | Yes | [Multi-Tenancy] Platform Admin Portal | data export | 5 | Winky
|  | Task | CT-11994 | Yes | [Multi-Tenancy] Tenant Admin Portal | System Log page | 3 | Sameera
|  | Task | CT-11987 | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Rex Review And Submission Integrate Testing. |  | Lily/Winky/Sameera |  | Need to confirm with Kexin
|  | Task | CT-11736 | Closed | [Multi-Tenancy] Platform Admin Portal | Address sensitive information vulnerabilities identified by CheckmarX. [Phase 1 - API-Keys and Passwords] |  |  |  | No need to test
Sprint3 | 26-Nov-2025 09-Dec-2026 | Task | CT-12737 | Yes | [Multi-Tenancy] Platform Admin Portal | [API] Create and Update tenant APIs | 3 | Lily
|  | Task | CT-12735 | Closed | [Multi-Tenancy] Platform Admin Portal | [Research] Reload secret items from AWS secret manager without pod restart | 3 |  |  | No need to test
|  | Task | CT-12734 | Yes | [Multi-Tenancy] Platform Admin Portal | [API] Tenant admin create and update APIs | 1 | Winky
|  | Task | CT-12732 | Yes | [Multi-Tenancy] Platform Admin Portal | [FrontEnd] Update Tenant Admin | 2 | Winky
|  | Task | CT-12731 | Yes | [Multi-Tenancy] Platform Admin Portal | [FrontEnd] Create Tenant Admin | 2 | Winky
|  | Task | CT-12730 | Yes | [Multi-Tenancy] Platform Admin Portal | [FrontEnd] Tenant admin page Search and Filters | 2 | Sameera
|  | Task | CT-12729 | Yes | [Multi-Tenancy] Platform Admin Portal | [FrontEnd] View Tenant Admins | 3 | Winky
|  | Task | CT-12708 | Closed | Tech Debt - Performance tuning FY26Q3 | Merge duplicated class - part 2 | 3 |  |  | Elwin confirmed no need to test, he will test it by himself
|  | Story | CT-12568 | Yes | [Multi-Tenancy] Platform Admin Portal | View Tenant Details | 3 | Lily
|  | Story | CT-12567 | Yes | [Multi-Tenancy] Platform Admin Portal | Edit Tenant Information | 2 | Lily
|  | Story | CT-12566 | Yes | [Multi-Tenancy] Platform Admin Portal | Add new Tenant Page Popup | 3 | Lily
|  | Story | CT-12269 | Yes | Rebrand SIMT to Research Exchange Curate | UI Updates: Completing Rebranding of SIMT to Curate | 2 | Sameera
|  | Task | CT-12261 | Yes | [Multi-Tenancy] Platform Admin Portal | Get and fill specific content of tenant in FE page based on tenant ID | 3 | Sameera
Sprint4 | 10-Dec-2025 23-Dec-2025 | Task | CT-13063 | Closed | Tech Debt - Performance tuning FY26Q4 | [Design] List all the realted date realted to the time zone |  |  |  | No need to test
|  | Task | CT-13034 | Closed | Tech Debt - Performance tuning FY26Q3 | Encrypt connect secret before saving to database |  |  |  | No need to test
|  | Story | CT-12896 | Yes | Rebrand SIMT to Research Exchange Curate | Email Updates: Completing Rebranding of SIMT to Curate |  | Sameera
|  | Story | CT-12726 | Yes | GE Overview Dashboard for Generic workflow | Consolidate Guest Editor Data Across Workflows |  | Winky
|  | Story | CT-12725 | Yes | GE Overview Dashboard for Generic workflow | Enforce Permission-Based Access |  | Lily
|  | Task | CT-12709 | Closed | Tech Debt - Performance tuning FY26Q3 | Merge duplicated class - part 3 |  |  |  | No need to test
|  | Task | CT-12708 | Closed | Tech Debt - Performance tuning FY26Q3 | Merge duplicated class - part 2 |  |  |  | No need to test
|  | Task | CT-12695 | In Development | [Multi-Tenancy] prod domain name configuration | Config the Prod domain name |  |  |  | No need to test
|  | Task | CT-12693 | Closed | Tech Debt - Performance tuning FY26Q3 | Address sensitive information vulnerabilities identified by CheckmarX. [Phase 2 - JWT and Private-keys] |  |  |  | No need to test
|  | Story | CT-12381 | Yes | GE Overview Dashboard for Generic workflow | Display Guest Editor Overview Dashboard for Generic Workflow |  | Lily
Sprint5 | Jan 6- Jan 20 | Story | CT-13070 |  | Generic SIP workflow MVP Phase 1 | [BE Ge Update] Manage SIP IN Ideation |  | Sameera
|  | Story | CT-13069 |  | Generic SIP workflow MVP Phase 1 | [BE Update] Manage SIP In Ideation |  | Sameera
|  | Task | CT-13033 |  | STEP is removing production details, allow blank fields in Curate | Allow blank PE/PM details in exported data from Curate |  | Sameera
|  | Task | CT-13032 |  | STEP is removing production details, allow blank fields in Curate | Allow blank PE/PM details in SI/P details page |  | Lily
|  | Story | CT-13007 | Released at Jan. 15 | Improvements - SIMT Consumes ReX Submission/Review Events | Update Rescind event consumed from Review |  | Winky
|  | Task | CT-12710 |  |  | Merge duplicated class - part 4 |  |  |  | No need to test
|  | Task | CT-12695 |  |  | Config the Prod domain name |  |  |  | No need to test
|  | Story | CT-12159 | Yes | Generic SIP workflow MVP Phase 1 | Create Special Issue Proposal Form |  | Winky
|  | Story | CT-12157 |  | Generic SIP workflow MVP Phase 1 | Support for Combined and Separate Role Assignments |  | Lily
|  | Story | CT-12156 | Yes | Generic SIP workflow MVP Phase 1 | Assign Journals to Proposal Manager |  | Winky
|  | Story | CT-11598 |  | Generic SIP workflow MVP Phase 1 | Create and manage SIP Overview and Dashboard |  | Sameera
|  | Story | CT-11577 |  | Generic SIP workflow MVP Phase 1 | Create Proposal Manager Role and Group |  | Lily

## FY26Q2
Sprint | Time | Ready for UAT | Epic | Type | ID | Title | DEV story point | Assignee | QA Man days | Comments
Sprint 1 | 7.30-8.13 |  |  | Story | CT-12167 | Improvement on SI Overview data export |  | Winky
|  | Closed | SIMT FY26 Q2 Improvements | Story | CT-12163 | Update SI Overview to Include Operations Lead when filter SIs based on Operations Lead |  | Sameera
|  | Yes | SIMT is being rebranded to Curate | Story | CT-12023 | Apply Curate branding to login page |  | Lily |  | Connect Login Page and one configuration page/ confirm what dev will do
|  | Yes | SIMT is being rebranded to Curate | Story | CT-12022 | Update app catalog entries and metadata |  | Lily |  | confirm with dev if need testing
|  |  | SIMT is being rebranded to Curate | Story | CT-12021 | Update URLs and configure redirects for Curate |  | Winky |  | Automation could cover it (Update domain url) Automation could cover it (Open SI /SIP detail page) Legacy URL redirect to new URL | section -> verify
|  | Yes | SIMT is being rebranded to Curate | Story | CT-12020 | Update system-generated email addresses |  | Lily |  | Reference CT-12019/check template in database/send from curate@researchexchange.com
|  | Yes | SIMT is being rebranded to Curate | Story | CT-12019 | Update email templates to reflect Curate branding |  | Sameera |  | https://confluence.wiley.com/display/CTC/SIMT+Alert+Task+Trigger+Timeline SIP Workflow Single reassign ops/ce (SCA SI) Bulk transfer ops/ce (SCA SI) Single reassign ops/ce/screener (SIP) Bulk transfer ops/ce/screener (SIP)
|  | Yes | SIMT is being rebranded to Curate | Story | CT-12018 | Replace all UI references from SIMT to Curate |  | Winky |  | SIP Web Form Page SIMT Header SIMT- Internal Page SIP Workflow related regression Oepn Generic SI Detail Page Open SCA SI Detail Page Open SIP Detail Page Open GE Detail Page Check design/PR
Sprint 2 |  | Yes | [Multi Tenancy] - Service separation | Story | CT-12172 | Generic SI service seperated from SI Service [Periodical Task] | 3 | Winky
|  | Yes | [Multi Tenancy] - Service separation | Story | CT-12171 | Generic SI service seperated from SI Service [Database Layer] | 3 | Sameera
|  | Yes | [Multi Tenancy] - Service separation | Story | CT-12170 | Generic SI service seperated from SI Service [Controller Layer] | 5 | Winky
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12158 | Table of t_tenant creation | 1 |  |  | Regression testing is not needed
|  | Closed | [Multi Tenancy] - Service separation | Story | CT-12153 | Modify pipeline for service segreation | 3 |  |  | No need to test
|  | Yes | [Multi Tenancy] - Service separation | Story | CT-12149 | Generic SI service seperated from SI Service [Service Layer] | 5 | Lily
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12048 | [Design] Identify tables that need append tenent id & implementation | 3 |  |  | Regression testing is not needed
|  | Closed | [Multi-Tenancy] CONNECT Integration | Task | CT-12037 | Multi-Tenant Request Routing with Host Preservation in Nginx | 2 |  |  | No need to test
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-11962 | Frontend Generic SI split | 3 | Sameera
Sprint3 |  | Closed | [Multi Tenancy] - Service separation | Task | CT-12340 | Generic SI - Frontend related change(only change the url) |  |  |  | Regression testing for Generic SI
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12339 | Generic SI - Review current impl and design on Generic SI service controller layer
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12338 | Generic SI - Swagger update for API gateway |  |  |  | No need to test
|  | Closed |  | Story | CT-12334 | [QA] Kafa event testing tasks from Sprint 2 |  | Huixin
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-12323 | Create new tables to store and send emails for generic workflow |  | Sameera |  | Regression testing
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-12322 | Rename log service to database-automation service |  |  |  | No need to test
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-12321 | Rename email service to integration service |  | Sameera |  | Regression testing -check email sending
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12320 | Migrate Rex message consume logic from SI service and generic SI service to integration service |  | Winky/Huixin |  | Regression testing
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-12319 | Decoupling Article Submission Functionality for Generic SI |  | Winky/Huixin |  | Covered by CT-12320
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-12318 | Generic SI - API design and impl in API gateway |  |  |  | Regression testing for Generic SI
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12316 | Add a demo tenant into t_tenant table |  |  |  | Not able to test
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12304 | Create a new table of t_tenant_sys_config |  |  |  | Not able to test
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12152 | Summary the config table which need an initial step when creating new tanant |  |  |  | Not able to test
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-11985 | [Impl][Generic SI]Identify tables that need append tenent id & implementation |  |  |  | Not able to test
|  | Closed |  | Task | CT-12300 | Clear up the temp tables and backup tables in the prod env database
|  | Yes | [Multi Tenancy] - Service separation | Task | CT-11962 | Frontend Generic SI split |  |  |  | Need to fix bug
Sprint4 |  | Closed (Task) | [Multi Tenancy] - Service separation | Task | CT-12417 | [QA] Testing work on multi tenancy - generic SI functionality |  | Winky Lily and Sameera |  | Regression test for all requests related with Generic SI for Wiley and PBJ
|  | Closed | SIMT FY26 Q2 Improvements | Task | CT-12362 | Batch update for bad data |  |  |  | No need to test
|  | Released | SIMT FY26 Q2 Improvements | Story | CT-12285 | Decommission Subject Group |  | Lily |  | Hint message under Report
|  | Yes | [Multi-Tenancy] CONNECT Integration | Task | CT-12039 | Refactoring Gateway Authentication and Move the JWT Generation Logic to User Service |  | Sameera |  | API testing -> login successfully is enough.(Check Automation results for user login functionality)
|  | Closed (Task) | [Multi-Tenancy] CONNECT Integration | Task | CT-12038 | Integrate tenant_id into logining token |  | Winky |  | QA team need do the API testing of request header
|  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-11991 | Step 5: Handing tenent_id in DB mapper layer |  | Lily |  | Confirmed with Elwin, need to ensure JM of PBJ can not see Generic SI created for Wiley
|  | Closed | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-11990 | Step 1: Resolve requests and get the tenent_id in gateway |  |  |  | No need to test
|  | Closed | [Multi-Tenancy] CONNECT Integration | Task | CT-11989 | Register new auth domain on CONNECT to support multi tenacy |  |  |  | No need to test
|  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-11966 | Step 4: SIMT Tenant ID - http request and openFeign config |  | Winky Lily and Sameera |  | Regression test for all requests related with Generic SI for Wiley and PBJ
|  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-11961 | Step 3.2: SIMT Tenant ID - sub threads propagation |  | Sameera and Huixin |  | Confirmed with Kexin, need to check emai send and event related with GenericSI for Wiley and PBJ
|  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-11960 | Step 3.1: SIMT Tenant ID - scheduled tasks processing |  | Sameera and Huixin |  | Confirmed with Kexin, we need to test event and email send related with Generic SI for Wiley and PBJ
Sprint5 |  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-12501 | Implement tenant-specific SI code generation for proper incremental numbering per tenant. |  | Lily |  | New case
|  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-12500 | Add tenant_id column to missing tables |  | Winky |  | Regression testing
|  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-12499 | Scheduled Task improvement |  | Sameera |  | Regression testing
|  | Yes | Keep the Lights On - FY26Q3 - 2 | Story | CT-12478 | Change Async API source from simt to curate |  | Winky |  | No need to test
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12384 | [Sprint4] User service Jenkins pipeline and infrastructure change |  |  |  | No need to test
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12373 | Frontend Generic SI split |  |  |  | No need to test
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12045 | Jenkins Pipeline Improvement for Dependency Management and Build Efficiency |  |  |  | No need to test
|  | Yes | [Multi-Tenancy] non-prod Domain name configuration | Task | CT-12043 | Migration of PBJ Tenant to a Dedicated Connect Domain |  | Sameera |  | Regression testing
|  | Closed | [Multi-Tenancy] User Role & Permission | Task | CT-12040 | DB Table change and preparation |  |  |  | No need to test
Sprint6 |  | Yes | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-12565 | Assess impact of tenantId injection on non-generic events and schedulers - [Phase 1] |  | Sameera/Winky/Lily |  | Regression mentioned job
|  | Closed(Task) | SIMT FY26 Q2 Improvements | Story | CT-12559 | SIMT API to include Submission Proposal Instructions and Submission Instructions |  | Winky |  | Design new case
|  | Yes | [Multi Tenancy] - Service separation | Story | CT-12531 | redirect no-permission uses to dedicated alert page instead of sip-web-form |  | Sameera |  | Design new case
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12529 | [Research] Rename package prefix name |  |  |  | No need to test
|  | Closed | [Multi-Tenancy] Data Segregation | Task | CT-12518 | [Impl] Curate Kafka event archive solution |  |  |  | No need to test
|  | Closed | [Multi Tenancy] - Service separation | Task | CT-12364 | Add tenant into logger |  |  |  | No need to test
|  | Yes | [Multi-Tenancy] Tenant Admin Portal | Task | CT-12053 | New Menu - Tenant Admin |  | Lily |  | Is able to see the menu, and there is no content
|  | Yes | [Multi-Tenancy] Journal meta data processing | Task | CT-12046 | Extend Journal Sync Logic to Support Multi-Tenant Data |  | Winky |  | Associate JM then user can see new journals, not moc journal
|  | Closed | [Multi-Tenancy] User Role & Permission | Task | CT-12041 | Service code change |  |  |  | No need to test
|  | Ready for release | [Multi-Tenancy] Tenant ID resolving & processing | Task | CT-11986 | Tenant-specific SI Code generation auto increase per year |  | Lily |  | Design new case

## FY26Q1
Sprint | Time | Type | ID | Title | DEV story point | Assignee | QA Man days | Comments
Sprint1 | 4.30-5.14 | Task | CT-11337 | QA automation development |  |  | 8
|  | Story | CT-11332 | [Design]Event change for new attributes of CFA workflow | 2
|  | Story | CT-11311 | FY25Q1 PROD Release Support | 2
|  | Story | CT-11305 | FY26Q1 - Sprint 1 PROD Support | 3
|  | Task | CT-11287 | PKG/NLP APIs Endpoint authentication method and credentials update | 2 | Lily | 1
|  | Task | CT-11286 | PKG/NLP APIs Endpoint update | 2 | Lily | 1
|  | Story | CT-11271 | Include SI Aims & Scope and SI Topics in SI Update Events | 0 | Huixin | 1
|  | Story | CT-11270 | Surface SI Topics in SI Details Section | 3 | Winky | 1
|  | Story | CT-11269 | Surface SI Aims & Scope in SI Details Section | 3 | Winky | 1
|  | Task | CT-11190 | [RBAC And Resource] Implementation of Generic Row-Level Permission Logic for Resources | 3 |  |  | No need verify
|  | Task | CT-11189 | [RBAC And Resource] Resource Data Structure Definition. | 3 |  |  | No need verify
|  | Story | CT-10999 | Filter STEP Product API on Tenant ID | 3 | Huixin | 1
Sprint2 |  | Task | CT-11338 | QA automation development
|  | Story | CT-11334 | Revise Pages: SSIP/USIP Workflows - Replace "Open Call for Papers" with "Content Commissioning Approach" | 3 | Winky | 1
|  | Story | CT-11333 | Revise pages: "Content Commissioning Approach" Attribute in SSIP and USIP Records | 3 | Lily | 1
|  | Story | CT-11321 | "Content Commissioning Approach" for In Progress SIPs | 3 | Sameera | 2
|  | Story | CT-11320 | USIP Workflow - Stage by Stage Behavior for "Potential Authors" Attribute | 0
|  | Story | CT-11319 | SSIP Workflow - Stage by Stage Behavior for "Potential Authors" Attribute | 0
|  | Story | CT-11317 | Exporting Potential Authors List | 3 | Sameera | 1
|  | Story | CT-11316 | Content Commissioning Approach - "Potential Authors" Attribute | 0
|  | Story | CT-11312 | Content Commissioning Approach - "Type of Call" Attribute | 0
|  | Story | CT-11306 | FY26Q1 - Sprint 2 PROD Support | 3
|  | Story | CT-11302 | "Content Commissioning Approach" Functionality for SSIP and USIP Records | 5 | Lily | 2
|  | Story | CT-11301 | USIP Workflow - Replace "Open Call for Papers" with "Content Commissioning Approach" | 0
|  | Story | CT-11300 | SSIP/USIP Workflows - Replace "Open Call for Papers" with "Content Commissioning Approach" | 5 | Winky | 2 | 1+4/1 read + 1 design +3 (120)
|  | Story | CT-11107 | [Design] Refuse to Consider decision from ReX Screening recorded in Submission Overview | 0
|  | Story | CT-11106 | [Design] Return to Draft decision from ReX Screening recorded in Submission Overview | 0
|  | Story | CT-11105 | [Implement] Rescind Withdraw, Return to Draft and Refuse to Consider decisions from ReX Review/Screening recorded in Submission Overview | 5 | Winky&Huixin | 1+1 | UI Check and Data check need 1m/d -- Winky Message Consume Check 1m/d -- Huixin
|  | Story | CT-11104 | [Design] Withdraw decision from ReX Review recorded in Submission Overview | 0
|  | Story | CT-11103 | [Design] Withdraw decision from ReX Screening recorded in Submission Overview | 0
|  | Story | CT-11102 | [Design] Rescind Withdraw, Return to Draft and Refuse to Consider decisions from ReX Review/Screening recorded in Submission Overview | 5 | Winky | 0 | This user story is the design tasks for CT-11105
Sprint3 |  | Task | CT-11339 | QA automation development
|  | Story | CT-11335 | Edit: "Content Commissioning Approach" in SI Details Page | 3 | Lily | 1
|  | Story | CT-11331 | Event change for new attributes of CFA workflow | 2 | Huixin | 1
|  | Story | CT-11324 | "Content Commissioning Approach" for In Progress SIs | 2 | Sameera
|  | Story | CT-11323 | Display: "Content Commissioning Approach" in SI Details Page | 5 | Lily | 1
|  | Story | CT-11322 | Content Commissioning Approaches Section During SI Aquisition Process | 5 | Winky | 1
|  | Story | CT-11597 | Update SIP Overview and Maintain SIP History for New Commissioning Attributes | 3 | Winky
|  | Story | CT-11617 | Potential Author improvement | 2 | Sameera
|  | Story | CT-11307 | FY26Q1 - Sprint 3 PROD Support | 3
|  | Task | CT-11278 | [Design]Separate Generic SI data with SCA SI data in database and API | 5
|  | Story | CT-11221 | SI Details Page - Acquired Date must be read-only | 2 | Sameera
Sprint4 |  | Task | CT-11736 | Add sensitive information detection in the SIMT Repo |  |  |  | Confirmed with Ming, require tested by the company's security department
|  | Story | CT-11672 | Update SI Overview for New Commissioning Attributes |  | Winky
|  | Story | CT-11438 | GE Invitation Flow |  | Lily
|  | Story | CT-11437 | GE Information Section |  | Lily
|  | Story | CT-11220 | USIP Process Log - Display email of user who submits SIP Form |  | Winky
|  | Story | CT-11078 | Change PostConstruct to ApplicationRunner |  | Winky |  | Regression
|  | Story | CT-11038 | Batch Update for Operations Lead/Commissioning Editor/Screener in SIP Workflow |  | Sameera
|  | Story | CT-11037 | Batch Update for Operations Lead in SI Workflow |  | Sameera
|  | Story | CT-11036 | Ops Lead Reassignment in SI Workflow |  | Winky
|  | Improvement | CT-11707 | Generic SI Workflow - SI Aims & Scope and Topics Display Improvement |  | Winky
|  | Task | CT-10474 | [CW] Configurable for some fields |  | Sameera |  | Regression
Sprint5 |  | Story | CT-11442 | GE Invitation Page |  | Lily
|  | Story | CT-11441 | GE Invitation Response |  | Lily
|  | Story | CT-11440 | GE Invitation Email |  | Sameera
|  | Story | CT-11439 | Automated Invitation Reminders |  | Winky
|  | Task | CT-11342 | QA automation development
|  | Story | CT-11309 | FY26Q1 - Sprint 5 PROD Support
|  | Improvement | CT-8582 | EBM Review - Individual EBM Page Improvements |  | Sameera
|  | Task | CT-11714 | Restrict email sending at non-prod env |  | Sameera
|  | Story | CT-11775 | Make Idea Date a Read-Only Field in SI Workflow |  | Lily
|  | Story | CT-11064 | Solution to stop users from creating duplicate SIs during SI Acquisition |  | Winky
Sprint 6 |  | Story | CT-11584 | SCA SI Workflow - Users able to filter SIs based on Operations Lead |  | Sameera
|  | Story | CT-11223 | Enable filtering in TAT Reporting |  | Sameera
|  | Story | CT-11222 | SI can be Shelved from Acquired Stage |  | Sameera
|  | Story | CT-10270 | Journal Accept Stage Reminders |  | Winky
|  | Story | CT-10269 | Journal Editor Review Stage Reminders |  | Winky
|  | Story | CT-10268 | EBM Review Invitations Reminders |  | Lily
|  | Story | CT-10267 | Post EBM Review Revisions Reminders |  | Lily
|  | Story | CT-10266 | Post Screening Revisions Reminders |  | Winky
|  | Story | CT-10265 | Ideation Revisions Reminders |  | Lily
|  | Story | CT-10264 | Automatic Revision Deadline Extension |  | Winky

## FY25Q4
Sprint | Time | Type | ID | Title | DEV story point | Assignee | Need QA Verify | Case Count
Sprint1 | Jan 23-Feb 12 | Story | CT-9415 | [Backend] Merge kafak producer and consumer Properties in a same file | 1 | Huixin
|  | Task | CT-10385 | [Design] - Rex Review- Analysis Rex Review Message | 1
|  | Task | CT-10388 | [Design] - Rex Review - DB Design to store the raw message and processed value | 1
|  | Task | CT-10222 | [Design] SI Report Analysis for Rex Review Message | 2
|  | Story | CT-10209 | Format Whole SIMT Code and Delete unused code | 1 | Sameera
|  | Task | CT-10381 | [Design] - Rex Submission - Analysis Rex Submission Message | 1
|  | Task | CT-10382 | [Design] - Rex Submission - DB Design to store the raw message and processed value | 1
|  | Task | CT-10220 | [Design] SI Report Analysis for Rex Submission Message | 2 | Huixin
|  | Task | CT-8932 | [E2E Research] SIMT Technical Roadmap for E2E technical standard compliance
|  | Story | CT-9379 | SIP Kafka Topic creation and connectivity testing for all envs
|  | Task | CT-10405 | [Design] New Si Overview Page | 3
|  | Task | CT-10403 | [Design] New Si Detail Display | 2
|  | Task | CT-10376 | [Design] New SI Trigger By Dead Line | 1
|  | Task | CT-10375 | [Design] New Si WorkFlow Define | 2
|  | Task | CT-10398 | [Design] New Si WorkFlow Executor | 2
|  | Task | CT-10372 | [Design]SIMT TraceId - prototype demo for request and log | 3
|  | Task | CT-10377 | [Design]SIMT TraceId - prototype demo for feign client and kafka | 2
Sprint2 |  | Story | CT-10436 | Add Immediate Launch Button in SI Workflows |  | Lily
|  | Story | CT-10415 | Update SI Stage Page - Submission Overview step - EEO System is ReX Review |  | Winky
|  | Task | CT-10400 | [Design] New Si Event Sender
|  | Task | CT-10399 | [Impl] SI Report Analysis for Rex Review Message |  | Sameera
|  | Task | CT-10397 | [Impl] SI Report Analysis for Rex Submission Message |  | Sameera
|  | Task | CT-10392 | [Design]SIMT TraceId - prototype demo for scheduled task
|  | Task | CT-10390 | [Design]SIMT TraceId - prototype demo for sub thread
|  | Task | CT-10384 | [Design] - Rex Submission - Application design to process Message
|  | Task | CT-10379 | [Design] - Rex Review- Application design to process Message
|  | Story | CT-10371 | [impl] Managing journals assigned to the Journal Manager role |  | Winky
|  | Story | CT-10244 | New Special Issue Overview Dashboard |  | Lily
|  | Story | CT-10243 | [impl] Create ability to assign journals to a Journal Manager |  | Winky
|  | Story | CT-10226 | [impl] Redesign the Special Issue menu section |  | Lily
|  | Story | CT-10225 | [impl] Create Journal Manager role and si:write-jm permission |  | Lily
|  | Story | CT-10224 | SI Detail Page - Submission Overview - EEO System is ReX Review |  | Winky
|  | Story | CT-9118 | Datafields required by Marketing from SIMT |  | Huixin
|  | Improvement | CT-10238 | Imporvement for the creation of SIP and SI |  | Sameera
|  | Task | CT-10422 | [Impl] Create API for generic SI |  | Sameera
|  | Story | CT-10189 | [Backend] Need a generic way to test the email var preparation.
|  | Story | CT-10149 | [Backend] Need a warpped service to process the send email progress. |  | Sameera
|  | Story | CT-10399 | Add CFP url and publication link in the SI Async API |  | Huixin
Sprint3 |  | Task | CT-10427 | New SI Details Page - Updating |  | Sameera | generic story, any
|  | Task | CT-10425 | [Implement] New Si WorkFlow Executor
|  | Task | CT-10423 | [Implement] New Si WorkFlow Define
|  | Task | CT-10421 | New SI Workflow - Delete Draft SI |  | Sameera | close- close test task, low priority
|  | Task | CT-10406 | [Design] Generic SI API
|  | Task | CT-10374 | [Design]SIMT TraceId - UT and Integration Test
|  | Story | CT-10370 | New SI Workflow - Draft Stage |  | Sameera | 2 high priority issues
|  | Story | CT-10348 | Updates to the SI Events API |  | Huixin
|  | Story | CT-10343 | New SI Workflow - Shelved Stage |  | Winky
|  | Story | CT-10342 | New SI Workflow - Published Stage |  | Winky
|  | Story | CT-10341 | New SI Workflow - Closed Stage |  | Winky | Verify the bug
|  | Story | CT-10340 | New SI Workflow - Submission and Review Stage |  | Winky
|  | Story | CT-10339 | New SI Workflow - Acquired Stage |  | Lily | Ming
|  | Story | CT-10274 | FY25Q4 - Sprint 3 PROD Support
|  | Story | CT-10271 | New SI Details Page - Displaying |  | Lily | different stage
|  | Task | CT-10247 | [Impl] New SI Overview - Create Page |  | Sameera | verify fixed defects
|  | Story | CT-10246 | New SI Overview - Table |  | Lily | priviledge/Elwin
|  | Story | CT-10245 | New SI Overview - Filter |  | Lily | Elwin
|  | Improvement | CT-10292 | User Management - Users should not be deleted if associated with In Progress SIPs/SIs |  | Winky
|  | Task | CT-10223 | [Implement] SIMT Consumes Events from ReX Submission |  | Huixin
|  | Task | CT-10221 | [Implement] SIMT Consumes Events from ReX Review |  | Huixin
|  | Task | CT-10378 | [Design]SIMT TraceId - Design each key points based on the prototype
|  | Task | CT-10198 | [DB] liquibase migration
Sprint4 |  | Task | CT-10493 | TraceID - select/filter on AWS cloudwatch |  | huixin
|  | Task | CT-10482 | [Impl] SIMT TraceId - scheduled tasks propagation |  | huixin
|  | Task | CT-10396 | Generic SI Async API design |  | Huixin
|  | Enhancement | CT-10853 | Solution for LeadGE role changing after the Submitted Stage - Scenario2 After Saving |  | Winky
|  | Enhancement | CT-9996 | Solution for LeadGE role changing after the Submitted Stage - Scenario1 revision submit |  | Lily
|  | Task | CT-10854 | Solution for LeadGE role changing after the Submitted Stage - Common Logic |  | Lily | no design
|  | Task | CT-10850 | New SI Workflow - Email Templates - sending and filling variables |  | Sameera
|  | Story | CT-10647 | [Improvement] EEO system changes to ReX Review after SI Acquisition |  | Winky
|  | Story | CT-10435 | TAT Reports - Breakdown between Ex-Hindawi and Wiley Journals |  | Winky | api test design
|  | Task | CT-10426 | [Implement] New Si Event Sender |  | Huixin
|  | Task | CT-10424 | [Implement] New SI Trigger By Dead Line |  | Huixin
|  | Story | CT-10355 | Ideation TAT Reporting |  | Lily | Yuxin, testing postpone to next
|  | Story | CT-10345 | SI Workflow - Extend Submission Deadline after the date has passed |  | Winky
|  | Story | CT-10344 | New SI Workflow - Email Templates |  | Sameera
|  | Task | CT-9846 | External User Email Template Updates |  | Sameera
|  | Story | CT-9541 | Remove the DB view in the simt |  | Sameera
Sprint5 |  | Story | CT-10434 | CE Chase Tracker - Add Ideation (Awaiting Revision) |  | Winky
|  | Story | CT-10433 | Include CE Review in CDS Chase Tracker |  | Winky
|  | Story | CT-10432 | SIP Reporting Filters Function - Backend |  | Sameera
|  | Story | CT-10431 | TAT Reporting Export Function |  | Sameera
|  | Story | CT-10430 | Interactive Numbers in Reporting Tables |  | Sameera
|  | Task | CT-10420 | [Design] - using internal link/page to display previous external pages
|  | Task | CT-10402 | [Impl] STEP Topic Switch to Product API |  | huixin
|  | Story | CT-10364 | Overall TAT Reporting |  | Winky
|  | Story | CT-10363 | SI Launch TAT Reporting |  | Lily
|  | Story | CT-10361 | JE Review TAT Reporting |  | Winky
|  | Story | CT-10360 | CE Review TAT Reporting |  | Winky
|  | Story | CT-10359 | EBM Review TAT Reporting |  | Lily
|  | Story | CT-10358 | Revision TAT Reporting |  | Lily
|  | Story | CT-10357 | Screening TAT Reporting |  | Lily
|  | Story | CT-10356 | Submitted TAT Reporting |  | Winky
|  | Story | CT-10429 | TAT Reporting Display Requirements |  | Winky
|  | Story | CT-10992 | SI Workflow - Journal Name/Journal Code Not Editable |  | Winky
|  | Story | CT-10979 | TAT Reporting Record Fiscal Year Data |  | Lili
|  | Story | CT-11042 | SIP Reporting Filters Function - Frontend |  | Sameera
|  | Task | CT-9511 | sync up the journal status with STEP |  | Huixin
|  | Task | CT-10967 | [FE]Common Multiselect box component
|  | Task | CT-10624 | [DB apply] liquibase migration
|  | Task | CT-10401 | [Discovery] STEP Topic Switch to Product API |  | huixin
Sprint6 |  | Story | CT-10362 | SI Acquisition TAT Reporting |  | Lily
|  | Story | CT-10433 | Include CE Review in CDS Chase Tracker |  | Winky
|  | Story | CT-10434 | CE Chase Tracker - Add Ideation (Awaiting Revision) |  | Winky
|  | Task | CT-9759 | Delete cv failed on SIP detail page GE information |  | Sameera
|  | Story | CT-10270 | Journal Accept Stage Reminders |  | Winky
|  | Story | CT-10269 | Journal Editor Review Stage Reminders |  | Winky
|  | Story | CT-10268 | EBM Review Invitations Reminders |  | Lily
|  | Story | CT-10267 | Post EBM Review Revisions Reminders |  | Lily
|  | Story | CT-10266 | Post Screening Revisions Reminders |  | Lily
|  | Story | CT-10265 | Ideation Revisions Reminders |  | Lily
|  | Story | CT-10264 | Automatic Revision Deadline Extension
|  | Task | CT-9758 | Delete cv at wrong moment on SIP detail page GE information |  | Sameera
|  | Task | CT-9370 | Integrate all file upload functions into one set of logic.

## FY25Q3
Sprint | Time | Type | ID | Title | DEV story point | Assignee | Need QA Verify | Case Count
Sprint1 |  |  | CT-9224 | FY25Q3 - Sprint 1 PROD Support
|  |  | CT-9070 | SI Acquisition - Open For Submission Date | 3 | Sameera |  |  | Huixin
|  |  | CT-9076 | Display journal EEO System in SI Detail page | 2 | Lily
|  |  | CT-9022 | Revise SI Set Up in Submission System Email | 3 | Lily
|  |  | CT-9091 | Set up a new SI email template for "Reminder on upcoming "Open for Submission Date"" | 3 | Sameera
|  |  | CT-9331 | Automatic SI Stage Update in relation to SI Open Event | 2 | Sameera
|  |  | CT-9266 | SI Details - Closed for Submission | 2 | Lily
|  |  | CT-9049 | SI Acquired Date is SI Acquisition Date | 2 | Winky |  | 4
|  |  | CT-9267 | Set up a new SI email template for "Reminder on upcoming "Submission Deadline"" | 2 | Winky |  | 8
|  |  | CT-9088 | Revise SI Title and GE Access Remove from Submission System | 2 | Winky |  | 18
|  |  | CT-9355 | [Research] Technical design of Async API for SIP Events API
|  |  | CT-9218 | [E2E Research] CONNECT Integration for all types of users
|  |  | CT-9402 | [Connect API] Simt all types of users authenticate in Connect
|  |  | CT-9403 | [Connect API] Simt all types of users synchronizes information from Connect.
|  |  | CT-8952 | [Tech] Front-end Components Analysis
|  |  | CT-9421 | [UIUX] Need a forbiden tips when the user have no promissions to view SIP detail page
|  |  | CT-8322 | Q2 release support
|  |  | CT-8372 | AWS Authorization configure for SE
|  |  | CT-9453 | Automation tasks
|  |  | CT-8932 | [E2E Research] SIMT Technical Roadmap for E2E technical standard compliance
|  |  | CT-9316 | Kafka work track
Sprint2 |  |  | CT-9225 | FY25Q3 - Sprint 2 PROD Support | 3
|  |  | CT-9405 | [SIP Detail Page] Unified permission verification | 5 | Lily
|  |  | CT-9404 | [New Role] User creation and role binding | 5 | Lily
|  |  | CT-9407 | [Email Template] SIP external link placeholder replace to revise/jeRevise link. | 2 | Sameera | sprint3
|  |  | CT-9291 | Refine how References are displayed across the SIP and SI workflows | 3 | Lily
|  |  | CT-8936 | SIP Form User Profile | 2 | Winky | sprint2 | 3
|  |  | CT-9015 | Marketing attribution on SIP form | 2 | Winky | sprint2 | 2
|  |  | CT-8832 | Expand "si:write-ops" permission to other SI stages | 3 | Lily | sprint2
|  |  | CT-8702 | Revise Content Commissioning Approaches in SI Acquisition | 3 | Sameera | sprint2
|  |  | CT-9223 | SIP - Open Call for Paper Updates | 2 | Winky | sprint2 | 8
|  |  | CT-9290 | Aims & Scope Requirement | 2 | Winky | sprint2 | 9
|  |  | CT-9195 | Ops Lead Reassignment | 3 | Sameera | sprint2
|  |  | CT-9194 | Automate SIP keyword generation via Auto-Tagger | 3 | Winky | sprint2 | 6
|  |  | CT-8963 | [Front-end Tech] SI Overview Page Performance Analysis and Optimization | 5 | Huixin
|  |  | CT-9379 | SIP Kafka Topic creation and connectivity testing for all envs |  | Huixin
|  |  | CT-7718 | prod DB dump pipeline
Sprint3 |  | Story | CT-9410 | CONNECT for Publisher |  | Lily
|  | Story | CT-9409 | Create Publisher permission and role |  | Lily
|  | Task | CT-9394 | Connect Over all design for permission
|  | Story | CT-9069 | SIMT User Profile Improvements | 3 | Winky | qihang | 5
|  | Story | CT-9068 | CONNECT for Wiley users |  | Winky | qihang | 11
|  | Story | CT-9066 | CONNECT for EBM |  | Lily
|  | Story | CT-9061 | Create EBM permission and role |  | Lily
|  | Story | CT-9055 | CONNECT for Journal-Editor |  | Winky |  | 14
|  | Story | CT-9054 | Create Journal-Editor permission and role |  | Winky |  | 10
|  | Story | CT-9051 | CONNECT for Co-GE |  | Sameera
|  | Story | CT-9045 | Create Guest Editor role and permissions |  | Sameera
|  | Story | CT-9042 | CONNECT for Lead-GE |  | Sameera
|  |  | CT-9610 | [New Role] One user corresponds to multiple roles. |  | Lily
Sprint4 |  | Task | CT-9722 | Maintaining user login status through Connect refresh token. |  | Winky |  | 1
|  | Task | CT-9606 | [SIP] Visibility of AI Acquisition button judge by the decision API |  | Lily |  |  | Regression testing
|  | Improvement | CT-9509 | Remove Co-GEs from the CC line of all email templates |  | Sameera
|  | Story | CT-9434 | Hide "Assign to Screener" button once initial Screener is assigned |  | Sameera
|  | Story | CT-9433 | Redesign Screener Reassignment |  | Sameera
|  | Story | CT-9419 | [existing user management change] add last login time in current user management page |  | Sameera
|  | Story | CT-9418 | [existing user management change] system admin after login from CONNECT, keep the same landing page - user management page |  | Lily
|  | Story | CT-9417 | [existing user management change] remove current login page - hCAPTCHA decommission |  | Sameera | regression cases
|  | Story | CT-9416 | [existing user management change] remove reset password button in user management page |  | Winky | Case include in CT-9069
|  | Story | CT-9415 | [existing user management change] [enhance system admin] in current user management page, system admin users can create, view, delete, update other system admin accounts, but set account zgao@wiley.com to read-only mode
|  | Story | CT-9414 | [existing user management change] [enhance system admin] create a pre-configured role - system admin in current role list which is read-only mode, permissions is same as current system admin
|  | Story | CT-9413 | [existing user management change] remove super admin feature |  | Winky |  | 9
|  | Story | CT-9383 | [Impl] SI Event sending - deleting |  | huixin
|  | Story | CT-9382 | [Impl] SIP Event sending - deleting |  | huixin
|  | Story | CT-9381 | [Impl] SIP Event sending - updating |  | huixin
|  | Story | CT-9380 | [Impl] SIP Event sending - creation |  | huixin
|  | Story | CT-9354 | New attribute: Curation Type (SI Acquisition) |  | Winky
|  | Story | CT-9352 | New attribute: Curation Type (SI Workflow) |  | Lily
|  | Story | CT-9118 | Datafields required by Marketing from SIMT |  | Huixin
|  |  | CT-9721 | Change request APIs for external SIP detail pages for CONNECT conversion |  | Sameera
|  | Task | CT-9713 | [Front-end Tech] SI Overview Page Performance Optimization - II |  | Winky
|  | Task | CT-8139 | [Front-end Tech] Lazy Load [Wrap up] + Router Refactor [Tech Design + Discussion + Implementation] |  | Lili | UI automation result check
|  | Task | CT-9877 | User Profile Panel to be shown to all users |  | Winky | assign to each owner
|  | Task | CT-9606 | [SIP] Visibility of SI Acquisition button is controlled by the decision API automatically |  | Lili
sprint5 |  | Task | CT-9265 | Move journal update kafka topic to the new topic |  | huixin
|  | Task | CT-10025 | External link pages use new unauthorized error pages |  | Winky |  | 8
|  | Story | CT-9561 | Need expose an API for QA member to trigger auto job in advance for API automation test |  | Winky
|  | Task | CT-9391 | Unified internal call: getCurrentUser() |  | Winky | api | sip related regression cases
|  | Task | CT-9374 | [FE]Mechanism of uniform code style |  | Winky | regression
|  | Story | CT-9118 | Datafields required by Marketing from SIMT |  | Huixin
|  | Story | CT-9358 | Expand AI Screening reporting |  | Lili | functional, tester Sameera
|  | Story | CT-9344 | Revise EBM Invitation Email |  | Lili | functional tester Lily
|  | Story | CT-9343 | Refine Cancel EBM Invitations |  | Lili | functional, tester Lily
|  | Story | CT-9342 | EBM Review - Manual EBM Invitation |  | Lili | tester Sameera
|  | Story | CT-9341 | EBM Review - EBM Suggestion Tool |  | Lili | tester Lily
|  | Story | CT-9340 | EBM Review Panel - Add "EBM Suggestion Tool" and "Manual EBM Invitation" Options |  | Lili | Tester Sameera
|  | Task | CT-8586 | [Frontend] Email Regex refactor |  | Winky | Email format related regression
|  | Task | CT-8428 | [Optimization] Duplicate API calls related to SIP module |  | Winky | api
|  | Task | CT-8324 | [Research] The front-end framework is stuck after the overall refresh: |  |  | regression
|  | Improvement | CT-8910 | EBM Review Panel Visibility |  | Sameera
Sprint6

## FY25Q2
Sprint | Time | Type | ID | Title | DEV story point | Assignee | Need QA Verify | Case Count
Sprint1 | 7/31-8/13 | Story | CT-8423 | Create script for batch update for existing SIPs after the FY25Q1 release | 5 | Lily
|  | Story | CT-8410 | FY25Q2 - Sprint 1 PROD Support | 3
|  | Story | CT-8409 | Q1 UAT Bugs Resolution | 8
|  | Task | CT-8433 | [Front-end] Upgrade Front-end Bundler | 2
|  | Task | CT-8352 | Whitelist configuration | 3
|  | Task | CT-8347 | Generate UUID for SI & SIP | 3 | Huixin
|  | Task | CT-8341 | [Design] SI event type defining | 3 | Huixin
|  | Task | CT-8340 | SI Topic creation | 1 | Huixin
|  | Task | CT-8336 | Migrate SIMT UAT ENVs to AWS Global | 5 | Lili
|  | Task | CT-8335 | Migrate SIMT data from AWS China to AWS Global[UAT] | 3
|  | Task | CT-8334 | Migrate SIMT domain name from wiley.cn to wiley.com | 5
|  | Task | CT-8332 | AWS Global Deployment ENV Preparation | 8
|  | Task | CT-7894 | [DESIGN] Generate UUID for SI & SIP | 2
|  | Task | CT-7893 | Migrate to STEP Product API | 3 | Huixin
Sprint2 | 8/14-8/27 | [7 empty] | verify -update successfully
|  | Story | CT-7806 | Upgrade Atypon PKG APIs for AI Screening features |  | Sameera |  |  | Regression | Perf test
|  | Story | CT-8417 | Migrate SIMT data from AWS China to AWS Global[PROD] | 3 | Winky
|  | Story | CT-8411 | FY25Q2 - Sprint 2 PROD Support | 3
|  | Story | CT-8300 | SSIP and USIP Workflow - Update Proposer Agree Email Templates | 1 | Lili/Winky |  | 2
|  | Story | CT-8298 | SSIP and USIP Workflow - Mutual Accept stage - SI Acquisition Updates | 3 | Lili/Winky |  | 4
|  | Story | CT-8297 | SSIP and USIP Workflow - Mutual Accept Stage - Remove ownership for CE and JPA | 1 | Lili/Winky |  | 8
|  | Story | CT-8295 | SSIP and USIP Workflow - Mutual Accept Stage - Change ownership to Ops Lead | 1 | Lili/Winky |  | 6
|  | Task | CT-8343 | [Design] SI updating event data model defining | 2 | Huixin
|  | Task | CT-8342 | [Design] SI creating data model defining | 5 | Huixin
|  | Task | CT-8141 | [Front-end] Add Safe Components/Error boundary | 3 | Winky |  | Exception mock | Regression
|  | Task | CT-7874 | [Configurable Workflow 5] Three types of workflow data definitions | 3
Sprint3 | 8/28-9/10 | Story | CT-8429 | Update and run script for batch update for existing SIPs after the FY25Q1 release | 3 | Lili
|  | Story | CT-8418 | Migrate SIMT data from AWS China to AWS Global[DEV&QA] | 3
|  | Story | CT-8416 | Migrate SIMT DEV&QA ENVs to AWS Global | 5
|  | Story | CT-8412 | FY25Q2 - Sprint 3 PROD Support | 3
|  | Story | CT-8303 | SI Workflow - Acquired Stage - Update Stage Email Notification | 1 | Sameera
|  | Story | CT-8302 | SI Workflow - Acquired Stage - Remove permission from Commissioning Editor | 2 | Winky |  | 7
|  | Story | CT-8301 | SI Workflow - Acquired Stage - Change ownership to Ops Lead | 3 | Lili |  | 7
|  | Story | CT-7531 | SI Workflow - Acquired Stage - Update Stakeholder Email Templates | 1 | Sameera
|  | Task | CT-8722 | SIMT Q1 release
|  | Task | CT-8352 | Whitelist configuration | 3
|  | Task | CT-8723 | [Design] SIMT Async API SI Data Modeling
|  | Task | CT-7715 | [Front-end] Decision panel Configurable components Migration | 5 | Lili
|  | Task | CT-8333 | Migrate SIMT PROD to AWS global env | 5 | Lili
|  | Task | CT-7873 | [Configurable Workflow 4] SIMT process data refactoring, and refresh historical data | 5 | Winky |  | 137
|  | Task | CT-8344 | Emitting SI creating event implementation | 3 | Huixin
|  | Task | CT-8326 | [Configurable Workflow 7 Design] SIMT integrated workflow control | 5
|  | Task | CT-8138 | [Front-end] Bundles Optimization | 5
|  | Task | CT-8705 | [Front-end] Safe Components/Error boundary Implementation |  | Winky
|  | Task | CT-8674 | Lazy load for user's alerts |  | Lili
|  | Task | CT-7875 | [Configurable Workflow 6] flow_common service workflow control APIs | 3
Sprint4 |  | Story | CT-8304 | SIP Reporting - Create Page under Report Menu | 1 | Chanaka
|  | Story | CT-7780 | SIP Reporting - CDS Chase Tracker | 5 | Winky |  | 19
|  | Story | CT-8837 | [Configurable Workflow 7-1] Refactoring of general flow logic | 5 | Lili | Chanaka
|  | Improvement | CT-8838 | [Configurable Workflow 7-2] Refactoring of special flow logic | 5 | Lili | Chanaka
|  | Improvement | CT-8839 | [Configurable Workflow 7-3] New Process flow API | 2 | Lili | Chanaka
|  | Improvement | CT-8840 | [Configurable Workflow 7-4] FrontEnd Switch to new process flow Api | 2 | Lili | Chanaka
|  | Task | CT-7937 | [Refinement] Response of Backend will include decision panel displaying flag | 2 | Lili
|  | Task | CT-8830 | Common Email Component - SSIP |  | Sameera
|  | Task | CT-8862 | [Login page]Fix the problem of too many nesting of MUI component |  | Chanaka
sprint5 | 9/11-9/25 | Story | CT-8367 | AI Screening Report - Record Number of errors per API | 2 | Lili | Sameera | 5
|  | Story | CT-8366 | AI Screening Report - Record Number of AI Screening Reports Downloaded | 2 | Lili | Sameera | 1
|  | Story | CT-8365 | AI Screening Report - Record Number of AI Screening Reports Generated | 3 | Sameera
|  | Story | CT-8364 | AI Screening Report - Record Number of SI Proposals Checked | 2 | Sameera
|  | Story | CT-8368 | AI Screening Report - Surface recorded events to relevant stakeholders | 3 | Lili | Sameera | 3
|  | Story | CT-8339 | Improvement - JE Revision and GE Revision Returned Email Templates | 1 | Winky | Chanaka | 2
|  | Task | CT-8345 | Emitting SI updating event implementation | 5 | Huixin
|  | Task | CT-8419 | [Front-end] Decision panel Configurable components Migration (USIP) | 3 | Lili | Chanaka
|  | Story | CT-8774 | SSIP - Direct Acquire Flow - Improvement | 1 | Sameera
|  | Story | CT-8613 | SIMT Keywords - Remove requirement from SIMT | 2 | Winky |  | 5
Sprint6 | 10/9-10/23 | Story | CT-8774 | SSIP - Direct Acquire Flow - Improvement | 1 | Sameera
|  | Story | CT-8613 | SIMT Keywords - Remove requirement from SIMT | 2 | Winky
|  | Story | CT-8367 | AI Screening Report - Record Number of errors per API | 2 | Lili | lili
|  | Task | CT-7711 | [DB reorg][implement] Discard t_sip_extend_ddl, merge to table 't_sip_external_link_logins' |  | Winky |  | 12 | regression
|  | Improvement | CT-8548 | Errors on Revision Form |  | Lili |  | 9
|  | Task | CT-9002 | [Front-end] Redefine Frontend Project Structure |  | Lili |  |  | regression
|  | Task | CT-8870 | Add Jest into frontend for Unit testing |  |  |  |  | Not need QA testing
|  | Story | CT-8420 | Add version info in the page | 3 | Sameera
|  | Story | CT-8307 | SIP Reporting - SIP Pipeline by Stages | 3 | Winky |  | 21
|  | Story | CT-8306 | SIP Reporting - CE Chase Tracker | 5 | Winky |  | 16
|  | Story | CT-8305 | SIP Reporting - Screener Chase Tracker | 5 | Winky |  | 8
|  | Task | CT-8830 | Common Email Component - SSIP |  | Sameera |  |  | regression
|  | Task | CT-8831 | Common Email Component - USIP | 2 | Chanaka | cc/bcc editable |  | regression
|  | Task | CT-8834 | Common Email Component - SI |  | Lili | confirm | 9 | regression
|  | Task | CT-9230 | [Async API]New event for SI opening |  | Huixin
|  | Task | CT-9036 | Test For kafka message sending |  | Huixin
|  | Task | CT-7707 | [DB reorg] uniqueness constraint missing | 2 | Winky |  |  | regression
|  | Story | CT-8311 | Create script to enable the migration of active SIPs from Salesforce to SIMT | 5 | Winky | Chanaka
|  | Task | CT-8391 | [Front-end] Redux Upgrade | 2
|  | Task | CT-8139 | [Front-end] Add Lazy loading modules - Design and Implementation for most value | 3

## FY25Q1
Sprint | ID | Title | DEV story point | Assignee | Case Count | Status |  | Sprint | Duration | QA | Capacity
Sprint 0 | CT-7434 | Click 'Tab' will change the focus element in login page. | 1 | Chanaka | 3 |  |  | Sprint1 | 5.2 -5.15 | Lili | 8 days
| CT-7401 | [M1][AI Screening Improvement] use ISSN number instead of journal name to find the journal from PKG API response | 1 | Lily | 3 |  |  |  |  | Winky | 8 days
| CT-7750 | User & System - Role Management - Create New Roles |  | Lily | 3
Sprint 1 | CT-7258 | SIP Workflow - New Permission Role - "sip:write-ops" | 5 | Lily | 17 |  |  |  |  | Chanaka | 5 days
| CT-7172 | SIP Status - New Attribute - Operations Lead | 2 | Lily | 9 |  |  |  |  | Sameera | 8 days
| CT-7440 | SIP Overview - Create - Operations Lead Filters & Columns - Solicited & Unsolicited Workflow | 2 | Chanaka | 64 |  |  | Sprint2 | 5.5 -5.28 | Lili | 8 days
| CT-7259 | SIP Workflow - New Permission Role - "sip:write-screener" | 3 | Winky | 29 |  |  |  |  | Winky | 8 days
| CT-7182 | SIP Status - New Attribute - Screener | 2 | Winky | 11 |  |  |  |  | Chanaka | 5 days
| CT-7441 | SIP Overview - Create - Filters & Columns - Solicited & Unsolicited Workflow | 2 | Winky | 16 |  |  |  |  | Sameera | 8 days
Sprint2 | CT-7261 | SIP Workflow - Update Permission Role - "sip:write-jpa" | 2 | Lily | 15 |  |  | Sprint3 | 5.29 -6.11 | Lili | 8 days
| CT-7767 | Ideation and Submitted Stages - Update Email Templates |  | Lily | 2
| CT-7260 | SIP Workflow - Update Permission Role - from "sip:write-handling-ce" to "sip:write-ce" | 2 | Winky | 29 |  |  |  |  | Winky | 8 days
| CT-7183 | SIP Status - Rename Attribute - Handling CE | 1 | Chanaka | 46 |  |  |  |  | Chanaka | 4 days
| CT-7201 | Ideation Stage - Changes - Decision Step- Solicited Workflow | 1 | Chanaka | 19 |  |  |  |  | Sameera | 8 days
| CT-7240 | Submitted Stage - Create Stage - Solicited Workflow | 3 | Lily | 2 |  |  | Sprint4 | 6.12-6.25 | Lili
| CT-7202 | Submitted Stage - Create - Decision Step - Solicited Workflow | 2 | Lily | 10 |  |  |  |  | Winky
| CT-7204 | Submitted Stage - Changes - Decision Step - Unsolicited Workflow | 3 | Winky | 6 |  |  |  |  | Chanaka
| CT-7205 | Submitted Stage - Remove - Checklist Step - Unsolicited Workflow | 2 | Winky | 2 |  |  |  |  | Sameera
Sprint3 | CT-7207 | Initial Review Stage - Create - Assign To Screener - Solicited & Unsolicited Workflow | 2 | Lily | 40 | Chunrui
| CT-7239 | Initial Review Stage - Create - Reassign Screener - Solicited & Unsolicited Workflow | 1 | Lily | 8 | Chunrui
| CT-7206 | Initial Review Stage - Changes - Checklist Attributes - Solicited & Unsolicited Workflow | 3 | Winky | 2
| CT-7249 | Initial Review Stage - Changes - Checklist Attributes - Solicited & Unsolicited Workflow | 1 | Winky | 2
| CT-7250 | Initial Review Stage - Checklist for GE - Add "Overall Publication Number" - Solicited & Unsolicited Workflow | 1 | Sameera | 22
| CT-7251 | Initial Review Stage - Checklist for GE - Add "Years of Research Experience " - Solicited & Unsolicited Workflow | 1 | Sameera | 26
| CT-7262 | Initial Review Stage - Checklist for GE - Add "Suspect/Predatory Editorial Roles" - Solicited & Unsolicited Workflow | 1 | Sameera | 38
| CT-7263 | Initial Review Stage - Checklist for GE - Update "Relevant Publication History" - Solicited & Unsolicited Workflow | 1 | Sameera | 20
| CT-7264 | Initial Review Stage - Update - Immediate Decision Section - Submitted & Unsubmitted Workflow | 1 | Sameera | 8
| CT-7222 | Initial Review Stage - Create - Complete Checklist - Solicited & Unsolicited Workflow | 1 | Winky | 18
| CT-7800 | Ideation Stage - Additional Attribute in Decision Panel - Solicited Workflow | 2 | Lily | 9
| CT-7224 | Initial Review Stage - Changes - Decision Step - Solicited Workflow | 3 | Lily | 21
| CT-7801 | Initial Review Stage - Changes - Decision Step - Unsolicited Workflow | 2 | Winky | 4
| CT-7243 | Initial Review Stage - Create - Cancel Revision Decision - Solicited & Unsolicited Workflow | 1 | Winky | 16
Sprint4 | CT-7225 | Commissioning Editor Review - Create Stage - Solicited Workflows | 3 | Winky | 9
| CT-7802 | Commissioning Editor Review - Create Stage - Unsolicited Workflows | 2 | Winky | 8
| CT-7565 | EBM Review Stage - Create - Solicited Workflow | 3 | Lily | 32 | Chunrui
| CT-7803 | EBM Review Stage - Create - Unsolicited Workflow | 2 | Lily | 33
| CT-7457 | EBM Review Stage - Create - EBM Review Individual Page - Solicited & Unsolicited Workflow | 2 | Lily | 8
| CT-7588 | Create the MVP SIP Form | 5 | Winky | 21
Sprint5 | CT-7223 | SIP Overview - Create - Filters - Checklist Status - Solicited & Unsolicited Workflows | 3 | Sameera | 32
| CT-7432 | SIP Overview - Filters - Update - SIP Stage - Solicited Workflow | 1 | Sameera | 3
| CT-7433 | SIP Overview - Filters - Update - SIP Stage - Unsolicited Workflow | 1 | Sameera | 3
| CT-7444 | SI Workflow - SI Detail Page - Stakeholders - Include Operations Lead | 1 | Lily | 3 | Chunrui
| CT-7445 | SI Workflow - SI Detail Page - Stakeholders - Include Screener | 1 | Lily | 3 | Chunrui
| CT-7766 | SI Workflow - SI Detail Page - Stakeholders - Update Handling CE | 1 | Lily | 3 | Chunrui
| CT-7996 | MVP SIP Form UI Tuning（Same case with CT-7588） | 2 | Winky | 0
| CT-7990 | SI Proposal Menu - SIP Report - Flagged GE Verification Page | 3 | Winky | 2
| CT-7993 | Improvement on SI Pipeline report to include newly added stages | 3 | Chanaka | 14
| CT-7997 | Revision Email Templates Updates | 2 | Winky | 12
| CT-8009 | Improvement USIP - Initial Review - Decision Panel when SIP Origin is CE Review （case added into CT-7802） | 1 | Winky | 0
| CT-7994 | Improvement to Reassign Screener Functionality | 1 | Lily | 4
Sprint 6 | CT-8274 | SIP - Initial Review Stage - View Checklist Button | 2 | Sameera
94
710
| 1384 |  |  | Lily | 225 |  | 4
|  |  |  | Winky | 187 | 160 | 4 |  |  | 160-200 | 800-1000
|  |  |  | Sameera | 152 | 57 | 2
|  |  |  | Chanaka | 143 | 60 | 2
|  |  | Winky | Regression for CT-7441 (SIP filter related) | 28 |  | Chanaka
|  |  |  | Regression for CT-7222(SIP checklist -- initial review) | 18 |  | Chanaka
|  |  |  | Regression for CT-7990(Flagged GE) | 50 |  | Winky
|  |  |  | Regression for USIP Workflow | 22 |  | Chanaka
|  | 351 |  | Total | 118
Sameera
Chunrui

## Tech_debt
ID | Title | DEV story point | Sprint | Status | QA | Case Count
CT-7727 | [Refactor][FE] Refine axios_instance.js and integrate authorization | 2 | Sprint2 | Done | Chanaka | 0
CT-7728 | [Refactor][FE] Refine SIP Filter Feature related files | 2 | Sprint2 | Ready for QA | Lily | 0 | Lily(SSIP) Winky(USIP)
| [Refactor][FE] Refine SIP Filter Feature related files (USIP) | 2 | Sprint2 | Ready for QA | Winky | 0
CT-7595 | Replace itextPDF with PDFBox | 2 | Sprint1 | Done | Chanaka | 2
CT-7600 | SI Overview list loading time performance tunning | 5 | Sprint5 | In Progress | Lily | 3
CT-7570 | Swagger Whitelabel Error Page |  | Sprint1 | Closed |  | 0
CT-7705 | [DB restructure] merge t_email_template_user to t_email_template | 1 | Sprint2 | Done | Lily | 6
CT-7706 | [DB restructure] Discard t_si_abnormal_edit_history | 1 | Sprint2 | Done | Lily | 4
CT-7709 | [DB restructure] sip_code generate logic | 2 | Sprint2 | Done | Winky | 1 | Need api automation cover it
CT-7712 | [DB restructure] Merge t_email_failed to t_email_history | 1 | Sprint2 | Done | Lily | 7
CT-7716 | [DB restructure] Discard t_api_secret | 1 | Sprint2 | Done | Lily | 11
CT-7720 | [DB restructure] SIP overview page optimize. | 3 | Sprint2 | Done | Winky | 7
CT-7724 | [DB reorg] Merge t_si_previouse_handling_ce to t_si | 2 | Sprint4 | Done | Winky | 4
CT-7593 | Enlarge the pod memory | 3 | 2 | DONE
CT-7471 | Create DB User in uat2,uat,dev,dev2,qa,qa2 environment | 2 | 1 | DONE
CT-7825 | [Refactor][FE] Refactor ideation stage of decision panel | 3 | 3 | DONE | Lily |  | Ideation CE Review and EBM Review decision panel
CT-7903 | [Design] Design document for decision panel on FE | 2 | 4 | DONE
CT-7596 | [Design]DB Restructure | 5 | 1 | DONE
CT-7597 | [Design] Configurable workflow | 8 | 2 | DONE
CT-7673 | Swagger api-docs | 1 | 2 | READY FOR QA
CT-7598 | [Design] SI and SIP Data migration to new workflow | 5 | 3 | DONE
CT-7599 | [Design] SIMT reporting impact analysis and solution for being compatible with the new workflow | 5 | 4 | DONE
CT-7870 | [Implementation][Configurable Workflow 1] flow dictionary definition of t_cw_stage_dict and t_cw_decision_dict | 2 | 4 | DONE |  |  | SSIP, USIP and SI workflow
CT-7871 | [Implementation][Configurable Workflow 2] Create a service flow_common, and create API to export the workflow dictionary. | 2 | 4 | DONE
CT-7872 | [Implementation][Configurable Workflow 3] Integrate workflow dictionary in flow_common to SIMT, and refresh the history data | 5 | 4 | DONE
CT-7333 | Upgrade JDK from 11 to 21 | 1 | 1 | DONE |  |  | ST for major feature
CT-7729 | [DB restructure][Design] Discard t_sip_checklist_initial, t_sip_checklist_initial_ge,t_sip_checklist_submitted,t_sip_checklist_submitted_ge | 3 | 2 | DONE
CT-7714 | [DB restructure][Design] t_sip_decision_field | 3 | 2 | DONE
CT-7717 | [DB restructure][design] Create t_cloud_file | 3 | 2 | DONE
CT-7719 | [DB restructure][design] Remove si_id in t_si | 2 | 2 | DONE
CT-7721 | [DB restructure][Design] Add id,create_time,update_time,create_by,update_by in tables | 1 | 2 | DONE
CT-7730 | [DB reorg][Implement] Remove si_id in t_si | 5 | Sprint3 | Done | Lily （Others） Winky （Marketing+ Publication） | 32 | Regression(Winky-24)(Lily-8)
CT-7826 | [Design] estimating compatibility of business requirements in Sprint3 with configurable workflow | 2 | 3 | Done
CT-7725 | [DB reorg] merge t_login_fail to t_user |  | Sprint5 | To Do |  | 8
CT-7726 | [DB reorg] merge t_user_reset_password to active_email |  | Sprint5 | To Do
CT-7711 | [DB reorg][implement] Discard t_inquiry_sip_assignee, t_sip_assign_to_editor, t_sip_journal_editor， t_sip_extend_ddl |  |  | To Do
CT-7713 | [DB reorg][Implement] Discard t_sip_checklist_initial, t_sip_checklist_initial_ge,t_sip_checklist_submitted,t_sip_checklist_submitted_ge |  | Sprint3 | Done | Winky | 0 | Refactor this feature in https://jira.wiley.com/browse/CT-7206
CT-7715 | [DB reorg][implement] t_sip_decision_field |  |  | To Do
CT-7718 | [DB reorg] [implement] t_cloud_file | 5 |  | To Do
CT-7723 | [DB reorg][implement] sys_config |  |  | To Do
CT-7804 | SIP External Link althriom need to use a safe way |  |  | To Do
92
[5 empty] | Lily | 31
[5 empty] | Winky | 24 | Execuld cases assign to Sameera
[5 empty] | Sameera | 11(Winky)
[5 empty] | Chanaka | 2
17,58可减，reression再考虑下，USIP workflow， 每个功能有个ST, Report